## 📋 Task Tracker
☀️ COURT MONITOR — PROJECT TRACKER
Solar-Powered Court Monitoring System ¦ dmpickleball.com ¦ Building in parallel — not yet deployed
# | Task | Owner | Status | Phase | Priority | Notes / Blockers
PHASE 1 — HARDWARE SETUP
1.1 | Purchase Android phone — Motorola Moto G 5G 2024 (XT2417D), used, unlocked, ~$50–$80 | 🙋 David | ⬜ Not Started | Phase 1 · Hardware | 🔴 High | Check Swappa, eBay, Facebook Marketplace. Must verify IMEI is clean + unlocked.
1.2 | Confirm phone is unlocked | 🙋 David | ⬜ Not Started | Phase 1 · Hardware | 🔴 High | Insert a non-original SIM to test, or run IMEI check online.
1.3 | Download Helium Mobile app on the target Android device | 🙋 David | ⬜ Not Started | Phase 1 · Hardware | 🔴 High | App required for account creation + activation.
1.4 | Create Helium Mobile account + sign up for Zero Plan (~3GB/mo free) | 🙋 David | ⬜ Not Started | Phase 1 · Hardware | 🔴 High | Do via app on the target device. helium.com for reference.
1.5 | Choose eSIM (instant) or physical SIM (shipped) — eSIM recommended | 🙋 David | ⬜ Not Started | Phase 1 · Hardware | 🔴 High | eSIM is fastest. Physical SIM = a few days shipping.
1.6 | Activate Helium line through app | 🙋 David | ⬜ Not Started | Phase 1 · Hardware | 🔴 High | Complete activation flow in-app.
1.7 | Confirm cellular data is working (turn off WiFi, load a website) | 🙋 David | ⬜ Not Started | Phase 1 · Hardware | 🔴 High | Verifies LTE is actually live before moving on.
1.8 | Purchase solar panel (~5W+, USB-C output) | 🙋 David | ⬜ Not Started | Phase 1 · Hardware | 🟡 Medium | Voltaic, Anker, or Amazon generic. Confirm USB-C (Moto G uses USB-C).
1.9 | Test solar panel charging the phone (30 min in direct sun) | 🙋 David | ⬜ Not Started | Phase 1 · Hardware | 🟡 Medium | Confirm it actually charges — cheap panels often underperform.
1.10 | Purchase weatherproof phone enclosure + fence mount | 🙋 David | ⬜ Not Started | Phase 1 · Hardware | 🟡 Medium | Amazon: search "outdoor phone mount fence waterproof". ~$20–40.
PHASE 2 — APP PROTOTYPE
2.1 | Decide: on-device AI vs. backend image analysis | 🙋 David | ⬜ Not Started | Phase 2 · App | 🔴 High | Recommendation: Backend (easier to update logic without redeploying app).
2.2 | Decide: React Native vs Kotlin for Android app | 🙋 David | ⬜ Not Started | Phase 2 · App | 🔴 High | Recommendation: React Native (JS, faster to build, easier to read).
2.3 | Create Supabase table: court_status (timestamp, occupied bool, image_url, confidence) | 🤖 Claude | ⬜ Not Started | Phase 2 · App | 🔴 High | SQL migration ready to run once decision made.
2.4 | Build Supabase Edge Function: POST /court-status (receives image + occupancy) | 🤖 Claude | ⬜ Not Started | Phase 2 · App | 🔴 High | Avoids Vercel 12-function limit. Better choice than a new /api/ file.
2.5 | Build Android app skeleton (camera + background service + API call) | 🤖 Claude | ⬜ Not Started | Phase 2 · App | 🔴 High | Awaiting framework decision (task 2.2).
2.6 | Implement periodic image capture (every 60–120 sec, screen off) | 🤖 Claude | ⬜ Not Started | Phase 2 · App | 🔴 High | Wide-angle, compressed before upload.
2.7 | Implement API call: compress image, POST to Supabase Edge Function | 🤖 Claude | ⬜ Not Started | Phase 2 · App | 🔴 High | Target <50KB per image.
2.8 | Install app on device + capture first test image | 🙋 David | ⬜ Not Started | Phase 2 · App | 🔴 High | Requires phone from Phase 1.
2.9 | Confirm backend receives image (check Supabase table) | 🙋 David | ⬜ Not Started | Phase 2 · App | 🔴 High | Claude will guide you exactly where to look.
PHASE 3 — AUTOMATION + OCCUPANCY LOGIC
3.1 | Decide: monitoring hours (e.g. 7am–9pm only, vs 24/7) | 🙋 David | ⬜ Not Started | Phase 3 · Automation | 🟡 Medium | Dawn-to-dusk saves power. 24/7 is simpler.
3.2 | Decide: do you want alerts? (e.g. court full >2 hrs) | 🙋 David | ⬜ Not Started | Phase 3 · Automation | 🟢 Low | Nice-to-have. Can be added later.
3.3 | Build occupancy detection logic (pixel-diff or ML) | 🤖 Claude | ⬜ Not Started | Phase 3 · Automation | 🔴 High | Start simple (brightness heuristic). Upgrade to ML if accuracy is low.
3.4 | Implement event-based send (only POST when status CHANGES) | 🤖 Claude | ⬜ Not Started | Phase 3 · Automation | 🔴 High | Dramatically reduces data usage. Stays well under 3GB/mo.
3.5 | Add daily keepalive ping (prevents Helium plan termination) | 🤖 Claude | ⬜ Not Started | Phase 3 · Automation | 🔴 High | Critical — Helium may cancel plan if ZERO data used in 30 days.
3.6 | Optimize image compression (target <50KB per image) | 🤖 Claude | ⬜ Not Started | Phase 3 · Automation | 🟡 Medium
3.7 | Set Android to kiosk/persistent mode (screen always off, app always running) | 🙋 David | ⬜ Not Started | Phase 3 · Automation | 🔴 High | Claude will write step-by-step instructions for this.
3.8 | Test occupancy accuracy — walk on/off court, watch dashboard | 🙋 David | ⬜ Not Started | Phase 3 · Automation | 🔴 High | Test day/night/shadow/different weather conditions.
PHASE 4 — ADMIN DASHBOARD TAB
4.1 | Design CourtMonitor tab layout (matches existing admin style) | 🤖 Claude | ⬜ Not Started | Phase 4 · Dashboard | 🟡 Medium | Inter font, brand green #1a3c34, matches AdminPanel component.
4.2 | Build CourtMonitorTab component in App.jsx | 🤖 Claude | ⬜ Not Started | Phase 4 · Dashboard | 🔴 High | Added to AdminPanel tab list (~line 2606 in App.jsx).
4.3 | Display: real-time status badge (OCCUPIED / EMPTY) + last-updated timestamp | 🤖 Claude | ⬜ Not Started | Phase 4 · Dashboard | 🔴 High | Big green/red indicator.
4.4 | Display: historical usage chart (occupancy by hour, last 7 days) | 🤖 Claude | ⬜ Not Started | Phase 4 · Dashboard | 🟡 Medium | Simple bar chart — no extra libraries needed.
4.5 | Display: latest snapshot image thumbnail (low-frequency) | 🤖 Claude | ⬜ Not Started | Phase 4 · Dashboard | 🟢 Low | Optional feature.
4.6 | Auto-refresh dashboard every 60 seconds (useEffect polling) | 🤖 Claude | ⬜ Not Started | Phase 4 · Dashboard | 🟡 Medium
4.7 | Deploy to production + verify on live site | 🙋 David | ⬜ Not Started | Phase 4 · Dashboard | 🔴 High | Git push from terminal → Vercel auto-deploys.
PHASE 5 — PHYSICAL DEPLOYMENT
5.1 | Scout mounting location at the court (fence post, height, sun exposure) | 🙋 David | ⬜ Not Started | Phase 5 · Deploy | 🔴 High
5.2 | Test camera angle before permanent mount (hold phone at planned spot, take photo) | 🙋 David | ⬜ Not Started | Phase 5 · Deploy | 🔴 High | Verify full court is captured from that height/angle.
5.3 | Install weatherproof enclosure on fence | 🙋 David | ⬜ Not Started | Phase 5 · Deploy | 🔴 High
5.4 | Mount phone in enclosure, angle camera at court | 🙋 David | ⬜ Not Started | Phase 5 · Deploy | 🔴 High | Secure it — verify it won't shift in wind.
5.5 | Connect solar panel, verify charging | 🙋 David | ⬜ Not Started | Phase 5 · Deploy | 🔴 High | Check battery is climbing/holding in direct sun.
5.6 | Confirm LTE signal at mounted location | 🙋 David | ⬜ Not Started | Phase 5 · Deploy | 🔴 High | Signal can vary — check bars at that exact spot.
5.7 | Start app, verify first live data appears in dashboard | 🙋 David | ⬜ Not Started | Phase 5 · Deploy | 🔴 High | The moment of truth 🎉
5.8 | Monitor for 48 hours — check for data gaps, battery drain, false detections | 🙋 David | ⬜ Not Started | Phase 5 · Deploy | 🔴 High

## 🛒 Shopping List
🛒 SHOPPING LIST — Court Monitor Hardware
# | Item | Est. Cost | Where to Buy | Status | Notes
1 | Motorola Moto G 5G 2024 (XT2417D) — used, unlocked | $50–$80 | Swappa, eBay, Facebook Marketplace | ⬜ Not Purchased | Verify IMEI clean. Must be unlocked.
2 | Solar panel, 5W+, USB-C output | $20–$40 | Amazon (Voltaic, Anker, or generic) | ⬜ Not Purchased | Confirm USB-C connector (not micro-USB).
3 | USB-C cable, short 1–2ft (weatherproof if possible) | $10–$15 | Amazon | ⬜ Not Purchased
4 | Weatherproof phone enclosure + outdoor fence mount | $20–$40 | Amazon — search: outdoor phone mount fence waterproof | ⬜ Not Purchased | Needs to allow clear camera view.
5 | Helium Mobile SIM (only if physical SIM chosen over eSIM) | Free | helium.com | ⬜ Not Purchased | eSIM is faster — skip this if going eSIM.
| ESTIMATED TOTAL | ~$100–$175 |  |  | Mid-range estimate: ~$130

## 🔓 Open Decisions
🔓 OPEN DECISIONS — Need David's Input Before Claude Can Build
# | Decision | Option A | Option B | Recommendation | David's Choice
1 | Android app framework | React Native (JavaScript) | Kotlin (Native Android) | React Native — JS, faster, David can read it
2 | Occupancy detection location | On-device (private, no upload) | Backend (easier to update) | Backend — update logic without redeploying app
3 | Backend API location | New Vercel function in /api/ | Supabase Edge Function | Supabase Edge Fn — avoids Vercel 12-fn limit
4 | Monitoring hours | 24/7 (simpler) | Dawn-to-dusk only (saves power) | Dawn-to-dusk — better for solar
5 | Court alerts | No alerts | Push/email if court full >X hours | No alerts for now, add later
6 | Data retention period | 30 days | 90 days | 90 days (good for usage pattern analysis)

## 📝 Session Log
📝 SESSION LOG — What Happened Each Chat
HOW TO USE: At the start of each chat, copy/paste this sheet into the conversation. Tell Claude what you've completed and what's changed.
Date | Session Summary | Tasks Completed | Tasks Blocked / Issues | Next Steps
2026-04-02 | Project kicked off. Full spec reviewed. Tracker created. | • Tracker file built • Handoff file read | • Awaiting hardware purchase (Phase 1) • Awaiting framework decision | David: start shopping list. Decide React Native vs Kotlin.